**Efficent Usage of Natural resources **

**2017-1-RO01-KA219-037131**

 ***Efficient Usage of Natural Resources***

 ***Transnational Meeting Agreed Actions***

***Malaga, Spain – 2nd & 3rd November 2017***

**Organisation of the mini projects**

It has been established that the mini projects will run and be coordinated according to the application form. Thus :

1. First mini project: Finding ways for the efficient usage of natural resources: Italy responsible for gathering information from all participating countries (by 1st of December 2017)
2. Second mini project: Finding ways for recycling – Romania responsible for gathering information by 1st of March 2018
3. Third mini project: Reducing carbon footprint - Turkey is responsible for gathering information from partners by May 2018
4. Fourth mini project: Photo Competition : Spain is responsible for gathering information from partners (Sept. 2018- Feb. 2019)
5. Fifth mini project: Shooting a short movie: Turkey 2019

**Timetable of the next LTTA and TPM**

It has been established that all partner countries will bring 4 students/country at all LTTA (as written in the application form) and they will be hosted in hosting families.

Dates for the next LTTA and TPM have been established, thus:

1. Italy LTTA: 4th-10th February 2018
2. Romania LTTA: 27th May-2nd June 2018
3. Romania TPM: 9th-13th September 2018

**What has been done**

* Logo competition and selection in every partner school and at internation level (TPM, Malaga, Spain) . The logo of the project is:



* Website of the project: <http://eco-partners.weebly.com>
* Partnerships with different institutions from the partner countries: universities, Botanical gardens, Environmental NGO-s, local authorities, etc
* Facebook Page: <https://www.facebook.com/racovitaromania/>
* Facebook closed group

**Further Actions**

* All partner countries are to send to the coordinator (Romania) a feed back about the website of the project by 15th of November 2017
* Creation of a Twin Space : Italy responsible (by 15th of November 2017)
* Test about Environment Awareness (Environmental Bahaviour Scale) to be taken by all students involved in the project (by 1st of December 2017)
* Creation of the Edmodo Class : Turkey responsible by 1st of

December 2017?

* Organising flash mobs at the same time in all partner countries (Romania responsible)